## Slide 1: Project Management with XPrince (2)
www.cs.put.poznan.pl/jnawrocki/require
Requirements Eng. & Project Management
Lecture 10
Jerzy Nawrocki
„Trabrennen” in Austria

## Slide 2: Agile software development – 90s
People & communication
Customer collaboration
Responding to change
Tommorow or never!
O K
Working software

## Slide 3: XPrince Team
XP
Prince 2
Kierownik Zespołu
Kierownik Zespołu
Project Board
Senior user
Executive
Senior Supplier
Manager = Coach
Project Assurance
Developers
Architect = Coach
Analyst=Client

## Slide 4: XPrince Lifecycle
16.10 | 27.11 | 23.01 | 8.04 | 27.05 | 17.06 | 8.07
Starting Up a Project | Aim and Scope | Architecture | Release 1 | Release 2 | Release 3 | Closing a Project
 | Business Modelling | Increment 1 | Increment 1 | Increment 1 | Increment 1 | 
 | Scope Elabor. | Increment 2 | Increment 2 | Increment 2 | Increment 2 | 
 |  |  | Transition | Transition | Transition | 
SU
IP
Stage
CL
Stage
Stage
Stage

## Slide 5: Team Growth
16.10 | 27.11 | 23.01 | 8.04 | 27.05 | 17.06 | 8.07
Starting Up a Project | Aim and Scope | Architec-ture | Release 1 | Release 2 | Release 3 | Closing a Project
Manager
Analyst
Architect + 1 Dev.
All the developers

## Slide 6: Presentation Plan
Introduction
Starting-up a project
Project logs
Architecture elaboration
„Trabrennen” in Austria

## Slide 7: Presentation Plan
Introduction
Starting-up a project
Project logs
Architecture elaboration
„Trabrennen” in Austria

## Slide 8: XPrince Lifecycle
16.10 | 27.11 | 23.01 | 8.04 | 27.05 | 17.06 | 8.07
Starting Up a Project | Aim and Scope | Architecture | Release 1 | Release 2 | Release 3 | Closing a Project
 | Business Modelling | Increment 1 | Increment 1 | Increment 1 | Increment 1 | 
 | Scope Elabor. | Increment 2 | Increment 2 | Increment 2 | Increment 2 | 
 |  |  | Transition | Transition | Transition | 

## Slide 9: Starting-up a Project (SU)
Project Exec and Project Manager
SU1
SU
Project Mandate
Design of a Project Management Team
SU2
Designation of the Project Manag. Team
SU3
Cust + PM
Project Brief
SU4
Cust + PM
Project Approach
SU5
Plan for Project Initiat.
SU6
PM
Supervisor
Notes: <number>

## Slide 10: Project Mandate
Customer name: ……………………………………
Customer representative: ………………………….
e-mail: …………………………………………….
phone: …………………………………………….
Project title: …………………………………………..

## Slide 11: Starting-up a Project (SU)
Project Exec and Project Manager
SU1
SU
Design of a Project Management Team
SU2
Designation of the Project Manag. Team
SU3
Cust + PM
Project Brief
SU4
Cust + PM
Project Approach
SU5
Plan for Project Initiat.
SU6
PM
Notes: <number>

## Slide 12: XPrince Team
XP
Prince 2
Kierownik Zespołu
Kierownik Zespołu
Project Board
Senior user
Executive
Senior Supplier
Manager
Project Assurance
Developers
Architect
Analyst

## Slide 13: Starting-up a Project (SU)
Project Exec and Project Manager
SU1
SU
Design of a Project Management Team
SU2
Management Team
Designation of the Project Manag. Team
SU3
Cust + PM
Project Brief
SU4
Project Approach
SU5
Plan for Project Initiat.
SU6
Notes: <number>

## Slide 14: Project Management Team
Executive: Jerzy Nawrocki
nawrocki@put.poznan.pl
(61) 665 29 80
Senior supplier: Bartosz Walter
bartosz.walter@cs.put.poznan.pl
(61) 665 29 80
Senior User: Executive

## Slide 15: Starting-up a Project (SU)
Project Exec and Project Manager
SU1
SU
Design of a Project Management Team
SU2
Designation of the Project Manag. Team
SU3
Cust + PM
Project Brief
SU4
Project Brief
Cust + PM
Project Approach
SU5
Plan for Project Initiat.
SU6
PM
Notes: <number>

## Slide 16: Metoda FAST / JAD
„Klient”
FAST =
Facilitated
Application
Specification
Technique
JAD
Joint
Application Development
Prowadzący
Analityk

## Slide 17: Agenda – Project Brief
Prolog
Meeting
Epilog
0 Participants and the agenda 5’
1 Customer characteristics 5’
2 What’s the problem? 15’
3 Who suffers? 5’
4 Impact of the problem 10’
5 Proposed solution 10’
6 Things to do 10’
Info for customer: Aim of the meeting (scope) + draft agenda
Questions: Participants? How long? (<90’) Time & place?
Report: Project title. Time & place of the meeting. Participants. Decisions made (next meeting?). Scope.
Ask for: Scope confirmation + opinion on feasability of the proj.

## Slide 18: Presentation Plan
Introduction
Starting-up a project
Project logs
Architecture elaboration
„Trabrennen” in Austria

## Slide 19: Project logs in PRINCE2 and XPrince
Risk log
Issue log
Quality log
Lessons-learned log

## Slide 20: Risk log
Short name
Description
Impact & probability
Risk monitoring
Risk avoidance
Contingency plan

## Slide 21: Risk management
Important:
Risk selection (impact & priority)
Risk owners (manager, architect, ..)

## Slide 22: Issue log
Change request
Off-specification
Problem
Question

## Slide 23: Quality log
Artefact
Author
Quality checking method
People involved
Dates (ready-to-check, accepted, ...)
Decision (accepted, rejected, ..)

## Slide 24: Presentation Plan
Introduction
Starting-up a project
Project logs
Architecture elaboration
„Trabrennen” in Austria

## Slide 25: Project Lifecycle
16.10 | 27.11 | 23.01 | 8.04 | 27.05 | 17.06 | 1.07
Starting | Initiat. | Stage1 | Stage2 | Stage3 | Stage4 | Closing
 | Inception 17.10-6.11 | Elaborat. 28.11-18.12 | Constr. 5 - 18.03 | Constr. 16-29.04 | Constr. 28.5-10.06 | 
 | Inception 7 - 27.11 | Elaborat. 5 - 23.01 | Constr. 19.03-1.04 | Constr. 7 – 20.05 | Transit. 11 - 17.06 | 
 |  |  | Transit. 2 - 8.04 | Transit. 21-27.05 |  | 

## Slide 26: Elaboration Objectives
1 Get a more detailed understanding of the requirements
2 Design, implement, validate, and baseline the arch-ture
3 Mitigate essential risks, and improve schedule/cost estim.
4 Refine the development case and make the tools ready

## Slide 27: Elaboration
1 Get a more detailed understanding of the requirements
Steps’ desc. of ~50% of Elabor. Ucs; decreasing priority
2 Design, implement, validate, and baseline the arch’ture
DI&T a few critical scenarios to identify architecture type and architecture mechanisms.
I&T an initial set of architecture mechanisms.
Do a preliminary logical database design.
3 Mitigate essential risks, and improve schedule/cost estim.
Identify possible performance problems and test them
First Iteration

## Slide 28: Elaboration
1 Get a more detailed understanding of the requirements
Steps’ desc. of remaining Elaboration’s Ucs
2 Design, implement, validate, and baseline the arch’ture
Fix first-iteration’s issues.
DI&T the remaining architecturally significant scenarios.
D&I a preliminary version of the database.
I&T remaining architectural mechanisms.
3 Mitigate essential risks, and improve schedule/cost estim.
Address technically high-risk issues: concurrency, distribution, performance, (external) interfaces.
Second Iteration

## Slide 29: Ideal Architect
Experience
Leadership
Communication
Goal-oriented and proactive

## Slide 30: Summary
At last!
Combination of agile methodology (XP) with disciplined ones (PRINCE 2 and RUP) is possible
Tool support (UC Workbench) is important
Flexible approach to pair programming

## Slide 31: Questions?
?
Notes: <number>